## README
TILLER BILLING COMPASS - DB IMPORT FILE
Generated from: Dashboard - TILLER _BILL RECEIVED.xlsx
IMPORT ORDER (DBeaver):
Step 1 | departments → no FKs
Step 2 | project_categories → no FKs
Step 3 | clients → no FKs
Step 4 | projects → needs clients, departments, project_categories
Step 5 | project_bills → needs projects
LEGEND:
🟡 YELLOW cells | DATA MISSING from Excel — fill before import
🔴 RED headers | Entire column missing from Excel — fill all rows
MISSING DATA SUMMARY:
clients | contact_person, contact_email, contact_phone — ALL NULL
departments | ENTIRE TABLE — not in Excel, inferred from project domain
project_categories | ENTIRE TABLE — not in Excel, inferred from project domain
projects | department_id, category_id, start_date, end_date, pg_* fields — ALL MISSING
project_bills | vat (100% null), it (99% null), received_percent, tentative_billing_date (52 null), received_amount/date (42-70 null)

## departments
id | name | description
1 | Development Research | GIZ-type development & research projects
2 | Urban Development | UDD/CDA/SCC/DNCC urban development projects
3 | Water & Sanitation | DPHE water & sanitation projects
4 | Water Supply | GWSC water supply projects

## project_categories
id | name | description
1 | Development Research | Baseline studies, research & development programs
2 | GIS & Survey | Geospatial, GIS survey and mapping projects
3 | Urban Planning | Urban master plans and upazila development plans
4 | Water & Sanitation | Water supply and sanitation infrastructure
5 | Water Supply | Water network and supply system projects

## clients
id | name | contact_person | contact_email | contact_phone
1 | CDA
2 | DNCC
3 | DPHE
4 | GIZ
5 | GWSC
6 | SCC
7 | UDD

## projects
id | project_name | client_id | department_id | category_id | start_date | end_date | total_project_value | status | pg_percent | pg_amount | pg_bank_share_percent | pg_user_deposit | pg_status | pg_clearance_date
1 | CDA | 1 | 2 | 2 |  |  | 31500000 | ONGOING |  |  |  |  | PENDING
2 | DEEW | 2 | 2 | 2 |  |  | 12380280 | ONGOING |  |  |  |  | PENDING
3 | 3River Project | 3 | 3 | 4 |  |  | 2800500 | ONGOING |  |  |  |  | PENDING
4 | Barebdra | 3 | 3 | 4 |  |  | 11100000 | ONGOING |  |  |  |  | PENDING
5 | Baseline | 4 | 1 | 1 |  |  | 1048621 | COMPLETED |  |  |  |  | PENDING
6 | INCLUDE | 4 | 1 | 1 |  |  | 25336110 | ONGOING |  |  |  |  | PENDING
7 | NSD | 5 | 4 | 5 |  |  | 55391520 | ONGOING |  |  |  |  | PENDING
8 | NSD-2 | 5 | 4 | 5 |  |  | 8000000 | ONGOING |  |  |  |  | PENDING
9 | Sylhet Master Plan | 6 | 2 | 3 |  |  | 36000000 | ONGOING |  |  |  |  | PENDING
10 | 12 Upz | 7 | 2 | 3 |  |  | 29222880 | ONGOING |  |  |  |  | PENDING
11 | 3Upz | 7 | 2 | 3 |  |  | 33928720 | ONGOING |  |  |  |  | PENDING
12 | 3upz TR | 7 | 2 | 3 |  |  | 4741974 | ONGOING |  |  |  |  | PENDING
13 | 3upz UAV | 7 | 2 | 2 |  |  | 9600000 | ONGOING |  |  |  |  | PENDING
14 | 9Upz | 7 | 2 | 3 |  |  | 23266291 | ONGOING |  |  |  |  | PENDING
15 | Meherpur | 7 | 2 | 3 |  |  | 67629465 | ONGOING |  |  |  |  | PENDING
16 | SRDP | 7 | 2 | 3 |  |  | 39365877 | COMPLETED |  |  |  |  | PENDING

## project_bills
id | project_id | sl_no | bill_name | bill_percent | bill_amount | tentative_billing_date | received_percent | received_amount | received_date | remaining_amount | vat | it | status | created_at
1 | 1 | 1 (a) | Inception (1 no) |  | 1000000 | 2022-10-23 |  | 1000000 | 2022-10-23 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
2 | 1 | 1 (b) | Draft Survey (1) |  | 1000000 | 2023-06-11 |  | 1000000 | 2023-06-11 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
3 | 1 | 1 (c) | Draft Survey (2) |  | 2500000 | 2023-06-22 |  | 2500000 | 2023-06-22 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
4 | 1 | 1 (d) | Draft Survey (3) |  | 2500000 | 2023-06-26 |  | 2500000 | 2023-06-26 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
5 | 1 | 1 (e) | Final Survey (1) |  | 1200000 | 2024-03-27 |  | 1200000 | 2024-03-27 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
6 | 1 | 1 (f) | Final Survey (2) |  | 2400000 | 2024-06-05 |  | 2400000 | 2024-06-05 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
7 | 1 | 1 (g) | Interim (1) |  | 2636000 | 2024-07-09 |  | 2636000 | 2024-07-09 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
8 | 1 | 1 (h) | Draft Final | 30 | 8505000 | 2025-06-15 |  | 600000 | 2025-07-09 | 7905000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
9 | 1 | 1 (i) | Final | 23 | 6520500 | 2025-12-15 |  | 900000 | 2026-02-26 | 5620500 |  |  | OUTSTANDING | 2026-03-05 16:04:09
10 | 1 | 1 (j) | retention | 10 | 3238500 | 2026-12-15 |  |  |  | 3238500 |  |  | OUTSTANDING | 2026-03-05 16:04:09
11 | 14 | 2 (a) | Mobilization (1 no) | 5 | 1093752 | 2022-07-04 |  | 1093752 | 2022-07-04 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
12 | 14 | 2 (b) | Inception (2 no) | 10 | 2187504 | 2023-06-11 |  | 2187504 | 2023-06-11 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
13 | 14 | 2 (c) | BaseMap 1 (half) | 5 | 1093752 | 2024-06-28 |  | 1093752 | 2024-01-03 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
14 | 14 | 2 (d) | BaseMap 2 (half) | 5 | 1180704 | 2024-06-28 |  | 1180704 | 2024-06-30 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
15 | 14 | 2 (e) | RTK Survey | 20 | 4722822 | 2024-06-28 |  | 4722822 | 2024-06-30 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
16 | 14 | 2 (f) | Draft Survey | 20 | 4722822 | 2024-11-13 |  | 4722822 | 2024-11-13 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
17 | 14 | 2 (g) | Final Survey | 10 | 2361410 | 2025-04-20 |  | 2361411 | 2025-06-24 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
18 | 14 | 2 (h) | Planning Assitance 1 | 10 | 2361410 | 2025-12-25 |  |  |  | 2361410 |  |  | OUTSTANDING | 2026-03-05 16:04:09
19 | 14 | 2 (i) | Planning Assitance 2 | 10 | 2361410 | 2026-03-25 |  |  |  | 2361410 |  |  | OUTSTANDING | 2026-03-05 16:04:09
20 | 14 | 2 (j) | web | 5 | 1180705 | 2026-06-25 |  |  |  | 1180705 |  |  | OUTSTANDING | 2026-03-05 16:04:09
21 | 16 | 3 (a) | Mobilization | 10 | 3836487 | 2024-03-31 |  | 3836487 | 2024-03-31 | 0 |  |  | PAID | 2026-03-05 16:04:09
22 | 16 | 3 (b) | Inception | 5 | 1973855 | 2024-06-09 |  | 1973855 | 2024-06-09 | 0 |  |  | PAID | 2026-03-05 16:04:09
23 | 16 | 3 (c) | BaseMap | 10 | 3947710 | 2024-11-24 |  | 3947710 | 2024-11-24 | 0 |  |  | PAID | 2026-03-05 16:04:09
24 | 16 | 3 (d) | Draft Survey | 20 | 7895420 | 2025-03-20 |  | 7895420 | 2025-03-04 | 0 |  |  | PAID | 2026-03-05 16:04:09
25 | 16 | 3 (e) | Final Survey | 15 | 5921565 | 2025-04-20 |  | 5921565 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 16:04:09
26 | 16 | 3 (f) | ASbuilt drawing | 15 | 5921565 | 2025-04-20 |  | 5921565 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 16:04:09
27 | 16 | 3 (g) | 3D Model | 25 | 9869275 | 2025-06-25 |  | 9869275 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 16:04:09
28 | 11 | 4 (a) | Mobilization 1 | 3 | 1608436 | 2024-06-30 |  | 1608436 | 2024-06-30 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
29 | 11 | 4 (b) | Mobilization 2 | 2 | 88000 | 2024-11-13 |  | 88000 | 2024-11-13 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
30 | 11 | 4 (c) | Inception | 10 | 3392872 | 2024-11-14 |  | 3392872 | 2024-11-14 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
31 | 11 | 4 (d) | Base Map | 15 | 5089308 | 2025-01-05 |  | 5089308 | 2025-01-05 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
32 | 11 | 4 (e) | Draft Survey | 25 | 8482180 | 2025-03-25 |  | 8482180 | 2025-06-05 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
33 | 11 | 4 (f) | Final Survey | 15 | 5089308 | 2025-05-25 |  | 5089308 | 2025-06-22 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
34 | 11 | 4 (g) | Interim | 10 | 3392872 | 2025-06-25 |  | 3392872 | 2025-06-22 | 0 |  | 3392872 | OUTSTANDING | 2026-03-05 16:04:09
35 | 11 | 4 (h) | Planning Assitance 1 | 10 | 3392872 | 2025-12-25 |  |  |  | 3392872 |  |  | OUTSTANDING | 2026-03-05 16:04:09
36 | 11 | 4 ( i) | Planning Assitance 2 | 10 | 3392872 | 2026-06-25 |  |  |  | 3392872 |  |  | OUTSTANDING | 2026-03-05 16:04:09
37 | 2 | 5 (a) | Inception report | 10 | 1238028 |  |  | 1238028 | 2024-11-20 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
38 | 2 | 5 (b) | Spatial database,planning report | 40 | 4952112 |  |  | 4389431 | 2025-04-15 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
39 | 2 | 5 (c) | Interim and Final report | 35 | 4333098 |  |  |  |  | 4333098 |  |  | OUTSTANDING | 2026-03-05 16:04:09
40 | 2 | 5 (d) | Supervision report | 15 | 1857042 |  |  |  |  | 1857042 |  |  | OUTSTANDING | 2026-03-05 16:04:09
41 | 7 | 6 (a) |  | 30 | 17433585 | 2024-07-24 |  | 17433585 | 2024-07-24 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
42 | 7 | 6 (b) |  | 20 | 11819199 | 2024-12-24 |  | 11819199 | 2024-12-24 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
43 | 7 | 6 (c) |  | 20 | 11819199 | 2025-03-31 |  | 6010675 | 2025-04-17 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
44 | 7 | 6 (d) |  | 20 | 11819199 | 2025-05-27 |  | 6028061 | 2025-11-06 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
45 | 7 | 6 (e) |  | 10 | 2500338 | 2025-08-25 |  | 15134406 | 2026-02-02 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
46 | 15 | 7 (a) | Mobilization | 10 | 6762947 | 2024-06-30 |  | 6762947 | 2024-06-30 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
47 | 15 | 7 (b) | Inception | 5 | 3381473 | 2024-07-30 |  | 3381473 | 2024-10-03 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
48 | 15 | 7 (c) | UAV image ,3D didgitize,database | 5 | 3381473 | 2024-09-23 |  | 3381474 | 2025-06-25 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
49 | 15 | 7 (d) | Base map,mouza map collection | 5 | 3381473 | 2024-10-14 |  | 3381474 | 2025-06-25 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
50 | 15 | 7 (e) | Interim report | 5 | 3381473 | 2025-06-22 |  | 3381474 | 2025-06-25 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
51 | 15 | 7 (f) | Draft survey report | 15 | 10144419 | 2025-08-28 |  | 10144421 |  | -2 |  |  | OUTSTANDING | 2026-03-05 16:04:09
52 | 15 | 7 (g) | Final Survey | 10 | 6762947 | 2025-12-30 |  | 6762947 | 2025-12-22 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
53 | 15 | 7 (h) | Planning Assistance 1 | 10 | 6762947 | 2026-12-29 |  | 6762947 | 2026-01-07 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
54 | 15 | 7 (i) | Planning Assistance 2 | 10 | 6762947 | 2025-06-30 |  |  |  | 6762947 |  |  | OUTSTANDING | 2026-03-05 16:04:09
55 | 15 | 7 (j) | Database management | 10 | 6762947 | 2025-12-15 |  |  |  | 6762947 |  |  | OUTSTANDING | 2026-03-05 16:04:09
56 | 15 | 7 (k) | 3D model preparation | 15 | 10144419 | 2025-09-22 |  |  |  | 10144419 |  |  | OUTSTANDING | 2026-03-05 16:04:09
57 | 6 | 8 (a) | Advance |  | 5067222 | 2025-02-10 |  | 4862022 | 2025-03-11 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
58 | 6 | 8 (b) | 1 no bill |  | 2533611 | 2025-05-31 |  | 2738811 | 2025-09-08 | -205200 |  |  | OUTSTANDING | 2026-03-05 16:04:09
59 | 6 | 8 (c) | 2 no bill |  | 5067222 | 2025-10-31 |  | 6882011 |  | -1814789 |  |  | OUTSTANDING | 2026-03-05 16:04:09
60 | 6 | 8 (d) | 3 no bill |  | 2533611 | 2026-02-15 |  |  |  | 2533611 |  |  | OUTSTANDING | 2026-03-05 16:04:09
61 | 6 | 8 (e) | 4 no bill |  | 2026888 | 2026-05-31 |  |  |  | 2026888 |  |  | OUTSTANDING | 2026-03-05 16:04:09
62 | 6 | 8 (f) | 5 no bill |  | 2026888 | 2026-10-31 |  |  |  | 2026888 |  |  | OUTSTANDING | 2026-03-05 16:04:09
63 | 6 | 8 (g) | 6 no bill |  | 2026888 | 2027-02-15 |  |  |  | 2026888 |  |  | OUTSTANDING | 2026-03-05 16:04:09
64 | 6 | 8 (h) | 7 no bill |  | 2026888 | 2027-05-31 |  |  |  | 2026888 |  |  | OUTSTANDING | 2026-03-05 16:04:09
65 | 6 | 8 (i) | 8 no bill |  | 2026892 | 2027-10-31 |  |  |  | 2026892 |  |  | OUTSTANDING | 2026-03-05 16:04:09
66 | 12 | 9 (a) | Mobilization | 10 | 474197 | 2025-03-30 |  | 362760 | 2025-04-16 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
67 | 12 | 9 (b) | Inception | 10 | 474197 | 2025-05-19 |  | 362760 | 2025-06-05 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
68 | 12 | 9 (c) | Survey Report | 15 | 711296.25 | 2025-06-16 |  |  |  | 711296.25 |  |  | OUTSTANDING | 2026-03-05 16:04:09
69 | 12 | 9 (d) | Interim | 25 | 1185493.75 | 2025-08-18 |  | 906903 |  | 278590.75 |  |  | OUTSTANDING | 2026-03-05 16:04:09
70 | 12 | 9 (e) | Prediction Model | 25 | 1185493.75 | 2025-12-30 |  |  |  | 1185493.75 |  |  | OUTSTANDING | 2026-03-05 16:04:09
71 | 12 | 9 (f) | Development plan | 15 | 711296.25 | 2026-05-18 |  |  |  | 711296.25 |  |  | OUTSTANDING | 2026-03-05 16:04:09
72 | 5 | 10 (c) | 3 no bill |  | 1048621 | 2025-09-30 |  | 1048621 | 2025-12-09 | 0 |  |  | PAID | 2026-03-05 16:04:09
73 | 13 | 12 |  |  | 9600000 | 2026-03-01 |  |  |  | 9600000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
74 | 10 | 13 (a) | 1st bill Mobilization | 5 | 1461144 |  |  | 1461144 | 2025-11-30 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
75 | 10 | 13 (b) | 2nd Bill Inception | 5 | 1461144 |  |  |  |  | 1461144 |  |  | OUTSTANDING | 2026-03-05 16:04:09
76 | 10 | 13 c | 3rd Bill Survey Report 1 | 25 | 7305720 |  |  |  |  | 7305720 |  |  | OUTSTANDING | 2026-03-05 16:04:09
77 | 10 | 13 d | 4th Bill Survey Report 2 | 20 | 5844576 |  |  |  |  | 5844576 |  |  | OUTSTANDING | 2026-03-05 16:04:09
78 | 10 | 13 e | 5th Bill | 10 | 2922288 |  |  |  |  | 2922288 |  |  | OUTSTANDING | 2026-03-05 16:04:09
79 | 10 | 13 f | 6th bill | 5 | 1461144 |  |  |  |  | 1461144 |  |  | OUTSTANDING | 2026-03-05 16:04:09
80 | 10 | 13 g | 7th bill | 5 | 1461144 |  |  |  |  | 1461144 |  |  | OUTSTANDING | 2026-03-05 16:04:09
81 | 10 | 13 h | 8th Bill | 5 | 1461144 |  |  |  |  | 1461144 |  |  | OUTSTANDING | 2026-03-05 16:04:09
82 | 10 | 13 i | 9th Bill | 10 | 2922288 |  |  |  |  | 2922288 |  |  | OUTSTANDING | 2026-03-05 16:04:09
83 | 10 | 13 j | 10th Bill | 10 | 2922288 |  |  |  |  | 2922288 |  |  | OUTSTANDING | 2026-03-05 16:04:09
84 | 9 | 14 a | Inception | 10 | 3600000 |  |  | 3521739 | 2026-02-23 | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
85 | 9 | 14 b | Survey Report | 25 | 9000000 |  |  |  |  | 9000000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
86 | 9 | 14 c | Draft Plan | 20 | 7200000 |  |  |  |  | 7200000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
87 | 9 | 14 4 | Final Plan | 20 | 7200000 |  |  |  |  | 7200000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
88 | 9 | 14 e | Feasibility Report | 25 | 9000000 |  |  |  |  | 9000000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
89 | 3 | 15a | 1st Bill | 30 | 821250 |  |  | 821250 |  | 0 |  |  | OUTSTANDING | 2026-03-05 16:04:09
90 | 3 | 15b | 2nd running Bill | 30 | 700000 |  |  |  |  | 700000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
91 | 3 | 15c | Final Bill | 40 | 1279250 |  |  |  |  | 1279250 |  |  | OUTSTANDING | 2026-03-05 16:04:09
92 | 4 | 16a | 1st Bill | 30 | 3500000 |  |  |  |  | 3500000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
93 | 4 | 16b | 2nd running Bill | 30 | 3500000 |  |  |  |  | 3500000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
94 | 4 | 16c | Final Bill | 40 | 4100000 |  |  |  |  | 4100000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
95 | 8 | 17a | 1st Bill | 30 | 2500000 |  |  |  |  | 2500000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
96 | 8 | 17b | 2nd running Bill | 30 | 2500000 |  |  |  |  | 2500000 |  |  | OUTSTANDING | 2026-03-05 16:04:09
97 | 8 | 17c | Final Bill | 40 | 3000000 |  |  |  |  | 3000000 |  |  | OUTSTANDING | 2026-03-05 16:04:09