## Project bill
SL | Client | Project Name | Bill Name | Bill percent | Bill Amount | Tentative Bill received month | Month | Year | Bill Received amount | Received Month | Remaining Bill | VAT | IT | Status
1 (a) | CDA | CDA | Inception (1 no) |  | 1000000 | 2022-10-23 | 2022-10-23 | 2022-10-23 | 1000000 | 2022-10-23 | 0 |  |  | Expense Complete Project Running
1 (b) | CDA | CDA | Draft Survey (1) |  | 1000000 | 2023-06-11 | 2023-06-11 | 2023-06-11 | 1000000 | 2023-06-11 | 0 |  |  | Expense Complete Project Running
1 (c) | CDA | CDA | Draft Survey (2) |  | 2500000 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2500000 | 2023-06-22 | 0 |  |  | Expense Complete Project Running
1 (d) | CDA | CDA | Draft Survey (3) |  | 2500000 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2500000 | 2023-06-26 | 0 |  |  | Expense Complete Project Running
1 (e) | CDA | CDA | Final Survey (1) |  | 1200000 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 1200000 | 2024-03-27 | 0 |  |  | Expense Complete Project Running
1 (f) | CDA | CDA | Final Survey (2) |  | 2400000 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2400000 | 2024-06-05 | 0 |  |  | Expense Complete Project Running
1 (g) | CDA | CDA | Interim (1) |  | 2636000 | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2636000 | 2024-07-09 | 0 |  |  | Expense Complete Project Running
1 (h) | CDA | CDA | Draft Final | 30% | 8505000 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 600000 | 2025-07-09 | 7905000 |  |  | Expense Complete Project Running
1 (i) | CDA | CDA | Final | 23% | 6520500 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 900000 | 2026-02-26 | 5620500 |  |  | Expense Complete Project Running
1 (j) | CDA | CDA | retention | 10% | 3238500 | 2026-12-15 | 2026-12-15 | 2026-12-15 |  |  | 3238500 |  |  | Expense Complete Project Running
2 (a) | UDD | 9Upz | Mobilization (1 no) | 5% | 1093752 | 2022-07-04 | 2022-07-04 | 2022-07-04 | 1093752 | 2022-07-04 | 0 |  |  | Expense Complete Project Running
2 (b) | UDD | 9Upz | Inception (2 no) | 10% | 2187504 | 2023-06-11 | 2023-06-11 | 2023-06-11 | 2187504 | 2023-06-11 | 0 |  |  | Expense Complete Project Running
2 (c) | UDD | 9Upz | BaseMap 1 (half) | 5% | 1093752 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 1093752 | 2024-01-03 | 0 |  |  | Expense Complete Project Running
2 (d) | UDD | 9Upz | BaseMap 2 (half) | 5% | 1180704 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 1180704 | 2024-06-30 | 0 |  |  | Expense Complete Project Running
2 (e) | UDD | 9Upz | RTK Survey | 20% | 4722822 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 4722822 | 2024-06-30 | 0 |  |  | Expense Complete Project Running
2 (f) | UDD | 9Upz | Draft Survey | 20% | 4722822 | 2024-11-13 | 2024-11-13 | 2024-11-13 | 4722822 | 2024-11-13 | 0 |  |  | Expense Complete Project Running
2 (g) | UDD | 9Upz | Final Survey | 10% | 2361410 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2361411 | 2025-06-24 | 0 |  |  | Expense Complete Project Running
2 (h) | UDD | 9Upz | Planning Assitance 1 | 10% | 2361410 | 2025-12-25 | 2025-12-25 | 2025-12-25 |  |  | 2361410 |  |  | Expense Complete Project Running
2 (i) | UDD | 9Upz | Planning Assitance 2 | 10% | 2361410 | 2026-03-25 | 2026-03-25 | 2026-03-25 |  |  | 2361410 |  |  | Expense Complete Project Running
2 (j) | UDD | 9Upz | web | 5% | 1180705 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 1180705 |  |  | Expense Complete Project Running | 5903525 | 9upz | 25%
3 (a) | UDD | SRDP | Mobilization | 10% | 3836487 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 3836487 | 2024-03-31 | 0 |  |  | Completed
3 (b) | UDD | SRDP | Inception | 5% | 1973855 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 1973855 | 2024-06-09 | 0 |  |  | Completed
3 (c) | UDD | SRDP | BaseMap | 10% | 3947710 | 2024-11-24 | 2024-11-24 | 2024-11-24 | 3947710 | 2024-11-24 | 0 |  |  | Completed
3 (d) | UDD | SRDP | Draft Survey | 20% | 7895420 | 2025-03-20 | 2025-03-20 | 2025-03-20 | 7895420 | 2025-03-04 | 0 |  |  | Completed
3 (e) | UDD | SRDP | Final Survey | 15% | 5921565 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 5921565 | 2025-04-30 | 0 |  |  | Completed
3 (f) | UDD | SRDP | ASbuilt drawing | 15% | 5921565 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 5921565 | 2025-04-30 | 0 |  |  | Completed
3 (g) | UDD | SRDP | 3D Model | 25% | 9869275 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 9869275 | 2025-04-30 | 0 |  |  | Completed | 0 | srdp | 0% | 0
4 (a) | UDD | 3Upz | Mobilization 1 | 3% | 1608436 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 1608436 | 2024-06-30 | 0 |  |  | Expense Complete Project Running
4 (b) | UDD | 3Upz | Mobilization 2 | 2% | 88000 | 2024-11-13 | 2024-11-13 | 2024-11-13 | 88000 | 2024-11-13 | 0 |  |  | Expense Complete Project Running
4 (c) | UDD | 3Upz | Inception | 10% | 3392872 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 3392872 | 2024-11-14 | 0 |  |  | Expense Complete Project Running
4 (d) | UDD | 3Upz | Base Map | 15% | 5089308 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 5089308 | 2025-01-05 | 0 |  |  | Expense Complete Project Running
4 (e) | UDD | 3Upz | Draft Survey | 25% | 8482180 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 8482180 | 2025-06-05 | 0 |  |  | Expense Complete Project Running
4 (f) | UDD | 3Upz | Final Survey | 15% | 5089308 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 5089308 | 2025-06-22 | 0 |  |  | Expense Complete Project Running
4 (g) | UDD | 3Upz | Interim | 10% | 3392872 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 3392872 | 2025-06-22 | 0 |  | 3392872 | Expense Complete Project Running
4 (h) | UDD | 3Upz | Planning Assitance 1 | 10% | 3392872 | 2025-12-25 | 2025-12-25 | 2025-12-25 |  |  | 3392872 |  |  | Expense Complete Project Running
4 ( i) | UDD | 3Upz | Planning Assitance 2 | 10% | 3392872 | 2026-06-25 | 2026-06-25 | 2026-06-25 |  |  | 3392872 |  |  | Expense Complete Project Running | 6785744 | 3upz | 20%
5 (a) | DNCC | DEEW | Inception report | 10% | 1238028 |  | 0 | 0 | 1238028 | 2024-11-20 | 0 |  |  | Expense Complete Project Running
5 (b) | DNCC | DEEW | Spatial database,planning report | 40% | 4952112 |  | 0 | 0 | 4389431 | 2025-04-15 | 0 |  |  | Expense Complete Project Running
5 (c) | DNCC | DEEW | Interim and Final report | 35% | 4333098 |  | 0 | 0 |  |  | 4333098 |  |  | Expense Complete Project Running
5 (d) | DNCC | DEEW | Supervision report | 15% | 1857042 |  | 0 | 0 |  |  | 1857042 |  |  | Expense Complete Project Running | 6190140 | DEEW
6 (a) | GWSC | NSD |  | 30% | 17433585 | 2024-07-24 | 2024-07-24 | 2024-07-24 | 17433585 | 2024-07-24 | 0 |  |  | Expense Complete Project Running
6 (b) | GWSC | NSD |  | 20% | 11819199 | 2024-12-24 | 2024-12-24 | 2024-12-24 | 11819199 | 2024-12-24 | 0 |  |  | Expense Complete Project Running
6 (c) | GWSC | NSD |  | 20% | 11819199 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 6010675 | 2025-04-17 | 0 |  |  | Expense Complete Project Running
6 (d) | GWSC | NSD |  | 20% | 11819199 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 6028061 | 2025-11-06 | 0 |  |  | Expense Complete Project Running
6 (e) | GWSC | NSD |  | 10% | 2500338 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 15134406 | 2026-02-02 | 0 |  |  | Expense Complete Project Running | 0 | NSD
7 (a) | UDD | Meherpur | Mobilization | 10% | 6762947 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 6762947 | 2024-06-30 | 0 |  |  | Expense Complete Project Running
7 (b) | UDD | Meherpur | Inception | 5% | 3381473 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 3381473 | 2024-10-03 | 0 |  |  | Expense Complete Project Running
7 (c) | UDD | Meherpur | UAV image ,3D didgitize,database | 5% | 3381473 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 3381474 | 2025-06-25 | 0 |  |  | Expense Complete Project Running |  |  | 10144419
7 (d) | UDD | Meherpur | Base map,mouza map collection | 5% | 3381473 | 2024-10-14 | 2024-10-14 | 2024-10-14 | 3381474 | 2025-06-25 | 0 |  |  | Expense Complete Project Running
7 (e) | UDD | Meherpur | Interim report | 5% | 3381473 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 3381474 | 2025-06-25 | 0 |  |  | Expense Complete Project Running
7 (f) | UDD | Meherpur | Draft survey report | 15% | 10144419 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 10144421 |  | -2 |  |  | Expense Complete Project Running
7 (g) | UDD | Meherpur | Final Survey | 10% | 6762947 | 2025-12-30 | 2025-12-30 | 2025-12-30 | 6762947 | 2025-12-22 | 0 |  |  | Expense Complete Project Running
7 (h) | UDD | Meherpur | Planning Assistance 1 | 10% | 6762947 | 2026-12-29 | 2026-12-29 | 2026-12-29 | 6762947 | 2026-01-07 | 0 |  |  | Expense Complete Project Running
7 (i) | UDD | Meherpur | Planning Assistance 2 | 10% | 6762947 | 2025-06-30 | 2025-06-30 | 2025-06-30 |  |  | 6762947 |  |  | Expense Complete Project Running
7 (j) | UDD | Meherpur | Database management | 10% | 6762947 | 2025-12-15 | 2025-12-15 | 2025-12-15 |  |  | 6762947 |  |  | Expense Complete Project Running
7 (k) | UDD | Meherpur | 3D model preparation | 15% | 10144419 | 2025-09-22 | 2025-09-22 | 2025-09-22 |  |  | 10144419 |  |  | Expense Complete Project Running | 23670311 | Meherpur | 70%
8 (a) | GIZ | INCLUDE | Advance |  | 5067222 | 2025-02-10 | 2025-02-10 | 2025-02-10 | 4862022 | 2025-03-11 | 0 |  |  | Running
8 (b) | GIZ | INCLUDE | 1 no bill |  | 2533611 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2738811 | 2025-09-08 | -205200 |  |  | Running
8 (c) | GIZ | INCLUDE | 2 no bill |  | 5067222 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 6882011 |  | -1814789 |  |  | Running
8 (d) | GIZ | INCLUDE | 3 no bill |  | 2533611 | 2026-02-15 | 2026-02-15 | 2026-02-15 |  |  | 2533611 |  |  | Running
8 (e) | GIZ | INCLUDE | 4 no bill |  | 2026888 | 2026-05-31 | 2026-05-31 | 2026-05-31 |  |  | 2026888 |  |  | Running
8 (f) | GIZ | INCLUDE | 5 no bill |  | 2026888 | 2026-10-31 | 2026-10-31 | 2026-10-31 |  |  | 2026888 |  |  | Running
8 (g) | GIZ | INCLUDE | 6 no bill |  | 2026888 | 2027-02-15 | 2027-02-15 | 2027-02-15 |  |  | 2026888 |  |  | Running
8 (h) | GIZ | INCLUDE | 7 no bill |  | 2026888 | 2027-05-31 | 2027-05-31 | 2027-05-31 |  |  | 2026888 |  |  | Running
8 (i) | GIZ | INCLUDE | 8 no bill |  | 2026892 | 2027-10-31 | 2027-10-31 | 2027-10-31 |  |  | 2026892 |  |  | Running | 10648066 | INCLUDE
9 (a) | UDD | 3upz TR | Mobilization | 10% | 474197 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 362760 | 2025-04-16 | 0 |  |  | Expense Complete Project Running
9 (b) | UDD | 3upz TR | Inception | 10% | 474197 | 2025-05-19 | 2025-05-19 | 2025-05-19 | 362760 | 2025-06-05 | 0 |  |  | Expense Complete Project Running
9 (c) | UDD | 3upz TR | Survey Report | 15% | 711296.25 | 2025-06-16 | 2025-06-16 | 2025-06-16 |  |  | 711296.25 |  |  | Expense Complete Project Running
9 (d) | UDD | 3upz TR | Interim | 25% | 1185493.75 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 906903 |  | 278590.75 |  |  | Expense Complete Project Running
9 (e) | UDD | 3upz TR | Prediction Model | 25% | 1185493.75 | 2025-12-30 | 2025-12-30 | 2025-12-30 |  |  | 1185493.75 |  |  | Expense Complete Project Running
9 (f) | UDD | 3upz TR | Development plan | 15% | 711296.25 | 2026-05-18 | 2026-05-18 | 2026-05-18 |  |  | 711296.25 |  |  | Expense Complete Project Running | 2886677 | 3UPZ
10 (c) | GIZ | Baseline | 3 no bill |  | 1048621 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 1048621 | 2025-12-09 | 0 |  |  | Completed | 0 | BASELINE-GIZ
12 | UDD | 3upz UAV |  |  | 9600000 | 2026-03-01 | 2026-03-01 | 2026-03-01 |  |  | 9600000 |  |  | Expense Complete Project Running
13 (a) | UDD | 12 Upz | 1st bill Mobilization | 5% | 1461144 |  | 0 | 0 | 1461144 | 2025-11-30 | 0 |  |  | Running
13 (b) | UDD | 12 Upz | 2nd Bill Inception | 5% | 1461144 |  |  | 0 |  |  | 1461144 |  |  | Running
13 c | UDD | 12 Upz | 3rd Bill Survey Report 1 | 25% | 7305720 | [5 empty] | 7305720 |  |  | Running | 56084463
13 d | UDD | 12 Upz | 4th Bill Survey Report 2 | 20% | 5844576 | [5 empty] | 5844576 |  |  | Running
13 e | UDD | 12 Upz | 5th Bill | 10% | 2922288 | [5 empty] | 2922288 |  |  | Running
13 f | UDD | 12 Upz | 6th bill | 5% | 1461144 | [5 empty] | 1461144 |  |  | Running
13 g | UDD | 12 Upz | 7th bill | 5% | 1461144 | [5 empty] | 1461144 |  |  | Running
13 h | UDD | 12 Upz | 8th Bill | 5% | 1461144 | [5 empty] | 1461144 |  |  | Running
13 i | UDD | 12 Upz | 9th Bill | 10% | 2922288 | [5 empty] | 2922288 |  |  | Running
13 j | UDD | 12 Upz | 10th Bill | 10% | 2922288 | [5 empty] | 2922288 |  |  | Running
14 a | SCC | Sylhet Master Plan | Inception | 10% | 3600000 |  |  |  | 3521739 | 2026-02-23 | 0 |  |  | Running
14 b | SCC | Sylhet Master Plan | Survey Report | 25% | 9000000 | [5 empty] | 9000000 |  |  | Running
14 c | SCC | Sylhet Master Plan | Draft Plan | 20% | 7200000 | [5 empty] | 7200000 |  |  | Running
14 4 | SCC | Sylhet Master Plan | Final Plan | 20% | 7200000 | [5 empty] | 7200000 |  |  | Running
14 e | SCC | Sylhet Master Plan | Feasibility Report | 25% | 9000000 | [5 empty] | 9000000 |  |  | Running
15a | DPHE | 3River Project | 1st Bill | 30% | 821250 |  |  |  | 821250 |  | 0 |  |  | Running
15b | DPHE | 3River Project | 2nd running Bill | 30% | 700000 | [5 empty] | 700000 |  |  | Running
15c | DPHE | 3River Project | Final Bill | 40% | 1279250 | [5 empty] | 1279250 |  |  | Running
16a | DPHE | Barebdra | 1st Bill | 30% | 3500000 | [5 empty] | 3500000 |  |  | Running
16b | DPHE | Barebdra | 2nd running Bill | 30% | 3500000 | [5 empty] | 3500000 |  |  | Running
16c | DPHE | Barebdra | Final Bill | 40% | 4100000 | [5 empty] | 4100000 |  |  | Running
17a | GWSC | NSD-2 | 1st Bill | 30% | 2500000 | [5 empty] | 2500000 |  |  | Running
17b | GWSC | NSD-2 | 2nd running Bill | 30% | 2500000 | [5 empty] | 2500000 |  |  | Running
17c | GWSC | NSD-2 | Final Bill | 40% | 3000000 | [5 empty] | 3000000 |  |  | Running
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Month = [Tentative Bill received month]
Year = [Tentative Bill received month]