## departments
id | name | description
1 | Survey | Survey
2 | GIS | Building and infrastructure architecture
3 | Planning | Business and technical consulting services
4 | Software Engineering | Software and hardware engineering projects

## project_categories
id | name | description
1 | Government
2 | Private
3 | International

## clients
id | name | contact_person | contact_email | contact_phone
1 | CDA
2 | DNCC
3 | DPHE
4 | GIZ
5 | GWSC
6 | SCC
7 | UDD

## projects
id | project_name | client_id | department_id | category_id | start_date | end_date | total_project_value | pg_percent | pg_amount | pg_bank_share_percent | pg_user_deposit | pg_status | pg_clearance_date | status
1 | CDA | 1 | 1 | 5 |  |  | 31500000 | [6 empty] | ONGOING
2 | 9Upz | 7 | 1 | 4 |  |  | 23266291 | [6 empty] | ONGOING
3 | SRDP | 7 | 1 | 4 |  |  | 39365877 | [6 empty] | ONGOING
4 | 3Upz | 7 | 1 | 4 |  |  | 33928720 | [6 empty] | ONGOING
5 | DEEW | 2 | 1 | 5 |  |  | 12380280 | [6 empty] | ONGOING
6 | NSD | 5 | 1 | 6 |  |  | 55391520 | [6 empty] | ONGOING
7 | Meherpur | 7 | 1 | 5 |  |  | 67629465 | [6 empty] | ONGOING
8 | INCLUDE | 4 | 1 | 5 |  |  | 25336110 | [6 empty] | ONGOING
9 | 3upz TR | 7 | 1 | 4 |  |  | 4741974 | [6 empty] | ONGOING
10 | Baseline | 4 | 1 | 5 |  |  | 1048621 | [6 empty] | ONGOING
11 | 3upz UAV | 7 | 1 | 4 |  |  | 9600000 | [6 empty] | ONGOING
12 | 12 Upz | 7 | 1 | 4 |  |  | 29222880 | [6 empty] | ONGOING
13 | Sylhet Master Plan | 6 | 1 | 4 |  |  | 36000000 | [6 empty] | ONGOING
14 | 3River Project | 3 | 1 | 6 |  |  | 2800500 | [6 empty] | ONGOING
15 | Barebdra | 3 | 1 | 6 |  |  | 11100000 | [6 empty] | ONGOING
16 | NSD-2 | 5 | 1 | 6 |  |  | 8000000 | [6 empty] | ONGOING

## project_bills
id | project_id | sl_no | bill_name | bill_percent | bill_amount | tentative_billing_date | received_percent | received_amount | received_date | remaining_amount | vat | it | status | created_at
1 | 1 | 1 (a) | Inception (1 no) | 3.17 | 1000000 | 2022-10-23 | 3.17 | 1000000 | 2022-10-23 | 0 |  |  | PAID | 2026-03-05 08:05:59
2 | 1 | 1 (b) | Draft Survey (1) | 3.17 | 1000000 | 2023-06-11 | 3.17 | 1000000 | 2023-06-11 | 0 |  |  | PAID | 2026-03-05 08:05:59
3 | 1 | 1 (c) | Draft Survey (2) | 7.94 | 2500000 | 2023-06-22 | 7.94 | 2500000 | 2023-06-22 | 0 |  |  | PAID | 2026-03-05 08:05:59
4 | 1 | 1 (d) | Draft Survey (3) | 7.94 | 2500000 | 2023-06-26 | 7.94 | 2500000 | 2023-06-26 | 0 |  |  | PAID | 2026-03-05 08:05:59
5 | 1 | 1 (e) | Final Survey (1) | 3.81 | 1200000 | 2024-03-27 | 3.81 | 1200000 | 2024-03-27 | 0 |  |  | PAID | 2026-03-05 08:05:59
6 | 1 | 1 (f) | Final Survey (2) | 7.62 | 2400000 | 2024-06-05 | 7.62 | 2400000 | 2024-06-05 | 0 |  |  | PAID | 2026-03-05 08:05:59
7 | 1 | 1 (g) | Interim (1) | 8.37 | 2636000 | 2024-07-09 | 8.37 | 2636000 | 2024-07-09 | 0 |  |  | PAID | 2026-03-05 08:05:59
8 | 1 | 1 (h) | Draft Final | 27 | 8505000 | 2025-06-15 | 1.9 | 600000 | 2025-07-09 | 7905000 |  |  | PARTIAL | 2026-03-05 08:05:59
9 | 1 | 1 (i) | Final | 20.7 | 6520500 | 2025-12-15 | 2.86 | 900000 | 2026-02-26 | 5620500 |  |  | PARTIAL | 2026-03-05 08:05:59
10 | 1 | 1 (j) | retention | 10.28 | 3238500 | 2026-12-15 | 0 |  |  | 3238500 |  |  | PENDING | 2026-03-05 08:05:59
11 | 2 | 2 (a) | Mobilization (1 no) | 4.7 | 1093752 | 2022-07-04 | 4.7 | 1093752 | 2022-07-04 | 0 |  |  | PAID | 2026-03-05 08:05:59
12 | 2 | 2 (b) | Inception (2 no) | 9.4 | 2187504 | 2023-06-11 | 9.4 | 2187504 | 2023-06-11 | 0 |  |  | PAID | 2026-03-05 08:05:59
13 | 2 | 2 (c) | BaseMap 1 (half) | 4.7 | 1093752 | 2024-06-28 | 4.7 | 1093752 | 2024-01-03 | 0 |  |  | PAID | 2026-03-05 08:05:59
14 | 2 | 2 (d) | BaseMap 2 (half) | 5.07 | 1180704 | 2024-06-28 | 5.07 | 1180704 | 2024-06-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
15 | 2 | 2 (e) | RTK Survey | 20.3 | 4722822 | 2024-06-28 | 20.3 | 4722822 | 2024-06-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
16 | 2 | 2 (f) | Draft Survey | 20.3 | 4722822 | 2024-11-13 | 20.3 | 4722822 | 2024-11-13 | 0 |  |  | PAID | 2026-03-05 08:05:59
17 | 2 | 2 (g) | Final Survey | 10.15 | 2361410 | 2025-04-20 | 10.15 | 2361411 | 2025-06-24 | 0 |  |  | PAID | 2026-03-05 08:05:59
18 | 2 | 2 (h) | Planning Assitance 1 | 10.15 | 2361410 | 2025-12-25 | 0 |  |  | 2361410 |  |  | OVERDUE | 2026-03-05 08:05:59
19 | 2 | 2 (i) | Planning Assitance 2 | 10.15 | 2361410 | 2026-03-25 | 0 |  |  | 2361410 |  |  | PENDING | 2026-03-05 08:05:59
20 | 2 | 2 (j) | web | 5.07 | 1180705 | 2026-06-25 | 0 |  |  | 1180705 |  |  | PENDING | 2026-03-05 08:05:59
21 | 3 | 3 (a) | Mobilization | 9.75 | 3836487 | 2024-03-31 | 9.75 | 3836487 | 2024-03-31 | 0 |  |  | PAID | 2026-03-05 08:05:59
22 | 3 | 3 (b) | Inception | 5.01 | 1973855 | 2024-06-09 | 5.01 | 1973855 | 2024-06-09 | 0 |  |  | PAID | 2026-03-05 08:05:59
23 | 3 | 3 (c) | BaseMap | 10.03 | 3947710 | 2024-11-24 | 10.03 | 3947710 | 2024-11-24 | 0 |  |  | PAID | 2026-03-05 08:05:59
24 | 3 | 3 (d) | Draft Survey | 20.06 | 7895420 | 2025-03-20 | 20.06 | 7895420 | 2025-03-04 | 0 |  |  | PAID | 2026-03-05 08:05:59
25 | 3 | 3 (e) | Final Survey | 15.04 | 5921565 | 2025-04-20 | 15.04 | 5921565 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
26 | 3 | 3 (f) | ASbuilt drawing | 15.04 | 5921565 | 2025-04-20 | 15.04 | 5921565 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
27 | 3 | 3 (g) | 3D Model | 25.07 | 9869275 | 2025-06-25 | 25.07 | 9869275 | 2025-04-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
28 | 4 | 4 (a) | Mobilization 1 | 4.74 | 1608436 | 2024-06-30 | 4.74 | 1608436 | 2024-06-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
29 | 4 | 4 (b) | Mobilization 2 | 0.26 | 88000 | 2024-11-13 | 0.26 | 88000 | 2024-11-13 | 0 |  |  | PAID | 2026-03-05 08:05:59
30 | 4 | 4 (c) | Inception | 10 | 3392872 | 2024-11-14 | 10 | 3392872 | 2024-11-14 | 0 |  |  | PAID | 2026-03-05 08:05:59
31 | 4 | 4 (d) | Base Map | 15 | 5089308 | 2025-01-05 | 15 | 5089308 | 2025-01-05 | 0 |  |  | PAID | 2026-03-05 08:05:59
32 | 4 | 4 (e) | Draft Survey | 25 | 8482180 | 2025-03-25 | 25 | 8482180 | 2025-06-05 | 0 |  |  | PAID | 2026-03-05 08:05:59
33 | 4 | 4 (f) | Final Survey | 15 | 5089308 | 2025-05-25 | 15 | 5089308 | 2025-06-22 | 0 |  |  | PAID | 2026-03-05 08:05:59
34 | 4 | 4 (g) | Interim | 10 | 3392872 | 2025-06-25 | 10 | 3392872 | 2025-06-22 | 0 |  | 3392872 | PAID | 2026-03-05 08:05:59
35 | 4 | 4 (h) | Planning Assitance 1 | 10 | 3392872 | 2025-12-25 | 0 |  |  | 3392872 |  |  | OVERDUE | 2026-03-05 08:05:59
36 | 4 | 4 ( i) | Planning Assitance 2 | 10 | 3392872 | 2026-06-25 | 0 |  |  | 3392872 |  |  | PENDING | 2026-03-05 08:05:59
37 | 5 | 5 (a) | Inception report | 10 | 1238028 |  | 10 | 1238028 | 2024-11-20 | 0 |  |  | PAID | 2026-03-05 08:05:59
38 | 5 | 5 (b) | Spatial database,planning report | 40 | 4952112 |  | 35.46 | 4389431 | 2025-04-15 | 0 |  |  | PAID | 2026-03-05 08:05:59
39 | 5 | 5 (c) | Interim and Final report | 35 | 4333098 |  | 0 |  |  | 4333098 |  |  | PENDING | 2026-03-05 08:05:59
40 | 5 | 5 (d) | Supervision report | 15 | 1857042 |  | 0 |  |  | 1857042 |  |  | PENDING | 2026-03-05 08:05:59
41 | 6 | 6 (a) |  | 31.47 | 17433585 | 2024-07-24 | 31.47 | 17433585 | 2024-07-24 | 0 |  |  | PAID | 2026-03-05 08:05:59
42 | 6 | 6 (b) |  | 21.34 | 11819199 | 2024-12-24 | 21.34 | 11819199 | 2024-12-24 | 0 |  |  | PAID | 2026-03-05 08:05:59
43 | 6 | 6 (c) |  | 21.34 | 11819199 | 2025-03-31 | 10.85 | 6010675 | 2025-04-17 | 0 |  |  | PAID | 2026-03-05 08:05:59
44 | 6 | 6 (d) |  | 21.34 | 11819199 | 2025-05-27 | 10.88 | 6028061 | 2025-11-06 | 0 |  |  | PAID | 2026-03-05 08:05:59
45 | 6 | 6 (e) |  | 4.51 | 2500338 | 2025-08-25 | 27.32 | 15134406 | 2026-02-02 | 0 |  |  | PAID | 2026-03-05 08:05:59
46 | 7 | 7 (a) | Mobilization | 10 | 6762947 | 2024-06-30 | 10 | 6762947 | 2024-06-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
47 | 7 | 7 (b) | Inception | 5 | 3381473 | 2024-07-30 | 5 | 3381473 | 2024-10-03 | 0 |  |  | PAID | 2026-03-05 08:05:59
48 | 7 | 7 (c) | UAV image ,3D didgitize,database | 5 | 3381473 | 2024-09-23 | 5 | 3381474 | 2025-06-25 | 0 |  |  | PAID | 2026-03-05 08:05:59
49 | 7 | 7 (d) | Base map,mouza map collection | 5 | 3381473 | 2024-10-14 | 5 | 3381474 | 2025-06-25 | 0 |  |  | PAID | 2026-03-05 08:05:59
50 | 7 | 7 (e) | Interim report | 5 | 3381473 | 2025-06-22 | 5 | 3381474 | 2025-06-25 | 0 |  |  | PAID | 2026-03-05 08:05:59
51 | 7 | 7 (f) | Draft survey report | 15 | 10144419 | 2025-08-28 | 15 | 10144421 |  | -2 |  |  | PAID | 2026-03-05 08:05:59
52 | 7 | 7 (g) | Final Survey | 10 | 6762947 | 2025-12-30 | 10 | 6762947 | 2025-12-22 | 0 |  |  | PAID | 2026-03-05 08:05:59
53 | 7 | 7 (h) | Planning Assistance 1 | 10 | 6762947 | 2026-12-29 | 10 | 6762947 | 2026-01-07 | 0 |  |  | PAID | 2026-03-05 08:05:59
54 | 7 | 7 (i) | Planning Assistance 2 | 10 | 6762947 | 2025-06-30 | 0 |  |  | 6762947 |  |  | OVERDUE | 2026-03-05 08:05:59
55 | 7 | 7 (j) | Database management | 10 | 6762947 | 2025-12-15 | 0 |  |  | 6762947 |  |  | OVERDUE | 2026-03-05 08:05:59
56 | 7 | 7 (k) | 3D model preparation | 15 | 10144419 | 2025-09-22 | 0 |  |  | 10144419 |  |  | OVERDUE | 2026-03-05 08:05:59
57 | 8 | 8 (a) | Advance | 20 | 5067222 | 2025-02-10 | 19.19 | 4862022 | 2025-03-11 | 0 |  |  | PAID | 2026-03-05 08:05:59
58 | 8 | 8 (b) | 1 no bill | 10 | 2533611 | 2025-05-31 | 10.81 | 2738811 | 2025-09-08 | -205200 |  |  | PAID | 2026-03-05 08:05:59
59 | 8 | 8 (c) | 2 no bill | 20 | 5067222 | 2025-10-31 | 27.16 | 6882011 |  | -1814789 |  |  | PAID | 2026-03-05 08:05:59
60 | 8 | 8 (d) | 3 no bill | 10 | 2533611 | 2026-02-15 | 0 |  |  | 2533611 |  |  | OVERDUE | 2026-03-05 08:05:59
61 | 8 | 8 (e) | 4 no bill | 8 | 2026888 | 2026-05-31 | 0 |  |  | 2026888 |  |  | PENDING | 2026-03-05 08:05:59
62 | 8 | 8 (f) | 5 no bill | 8 | 2026888 | 2026-10-31 | 0 |  |  | 2026888 |  |  | PENDING | 2026-03-05 08:05:59
63 | 8 | 8 (g) | 6 no bill | 8 | 2026888 | 2027-02-15 | 0 |  |  | 2026888 |  |  | PENDING | 2026-03-05 08:05:59
64 | 8 | 8 (h) | 7 no bill | 8 | 2026888 | 2027-05-31 | 0 |  |  | 2026888 |  |  | PENDING | 2026-03-05 08:05:59
65 | 8 | 8 (i) | 8 no bill | 8 | 2026892 | 2027-10-31 | 0 |  |  | 2026892 |  |  | PENDING | 2026-03-05 08:05:59
66 | 9 | 9 (a) | Mobilization | 10 | 474197 | 2025-03-30 | 7.65 | 362760 | 2025-04-16 | 0 |  |  | PAID | 2026-03-05 08:05:59
67 | 9 | 9 (b) | Inception | 10 | 474197 | 2025-05-19 | 7.65 | 362760 | 2025-06-05 | 0 |  |  | PAID | 2026-03-05 08:05:59
68 | 9 | 9 (c) | Survey Report | 15 | 711296.25 | 2025-06-16 | 0 |  |  | 711296.25 |  |  | OVERDUE | 2026-03-05 08:05:59
69 | 9 | 9 (d) | Interim | 25 | 1185493.75 | 2025-08-18 | 19.13 | 906903 |  | 278590.75 |  |  | PARTIAL | 2026-03-05 08:05:59
70 | 9 | 9 (e) | Prediction Model | 25 | 1185493.75 | 2025-12-30 | 0 |  |  | 1185493.75 |  |  | OVERDUE | 2026-03-05 08:05:59
71 | 9 | 9 (f) | Development plan | 15 | 711296.25 | 2026-05-18 | 0 |  |  | 711296.25 |  |  | PENDING | 2026-03-05 08:05:59
72 | 10 | 10 (c) | 3 no bill | 100 | 1048621 | 2025-09-30 | 100 | 1048621 | 2025-12-09 | 0 |  |  | PAID | 2026-03-05 08:05:59
73 | 11 | 12 |  | 100 | 9600000 | 2026-03-01 | 0 |  |  | 9600000 |  |  | OVERDUE | 2026-03-05 08:05:59
74 | 12 | 13 (a) | 1st bill Mobilization | 5 | 1461144 |  | 5 | 1461144 | 2025-11-30 | 0 |  |  | PAID | 2026-03-05 08:05:59
75 | 12 | 13 (b) | 2nd Bill Inception | 5 | 1461144 |  | 0 |  |  | 1461144 |  |  | PENDING | 2026-03-05 08:05:59
76 | 12 | 13 c | 3rd Bill Survey Report 1 | 25 | 7305720 |  | 0 |  |  | 7305720 |  |  | PENDING | 2026-03-05 08:05:59
77 | 12 | 13 d | 4th Bill Survey Report 2 | 20 | 5844576 |  | 0 |  |  | 5844576 |  |  | PENDING | 2026-03-05 08:05:59
78 | 12 | 13 e | 5th Bill | 10 | 2922288 |  | 0 |  |  | 2922288 |  |  | PENDING | 2026-03-05 08:05:59
79 | 12 | 13 f | 6th bill | 5 | 1461144 |  | 0 |  |  | 1461144 |  |  | PENDING | 2026-03-05 08:05:59
80 | 12 | 13 g | 7th bill | 5 | 1461144 |  | 0 |  |  | 1461144 |  |  | PENDING | 2026-03-05 08:05:59
81 | 12 | 13 h | 8th Bill | 5 | 1461144 |  | 0 |  |  | 1461144 |  |  | PENDING | 2026-03-05 08:05:59
82 | 12 | 13 i | 9th Bill | 10 | 2922288 |  | 0 |  |  | 2922288 |  |  | PENDING | 2026-03-05 08:05:59
83 | 12 | 13 j | 10th Bill | 10 | 2922288 |  | 0 |  |  | 2922288 |  |  | PENDING | 2026-03-05 08:05:59
84 | 13 | 14 a | Inception | 10 | 3600000 |  | 9.78 | 3521739 | 2026-02-23 | 0 |  |  | PAID | 2026-03-05 08:05:59
85 | 13 | 14 b | Survey Report | 25 | 9000000 |  | 0 |  |  | 9000000 |  |  | PENDING | 2026-03-05 08:05:59
86 | 13 | 14 c | Draft Plan | 20 | 7200000 |  | 0 |  |  | 7200000 |  |  | PENDING | 2026-03-05 08:05:59
87 | 13 | 14 4 | Final Plan | 20 | 7200000 |  | 0 |  |  | 7200000 |  |  | PENDING | 2026-03-05 08:05:59
88 | 13 | 14 e | Feasibility Report | 25 | 9000000 |  | 0 |  |  | 9000000 |  |  | PENDING | 2026-03-05 08:05:59
89 | 14 | 15a | 1st Bill | 29.33 | 821250 |  | 29.33 | 821250 |  | 0 |  |  | PAID | 2026-03-05 08:05:59
90 | 14 | 15b | 2nd running Bill | 25 | 700000 |  | 0 |  |  | 700000 |  |  | PENDING | 2026-03-05 08:05:59
91 | 14 | 15c | Final Bill | 45.68 | 1279250 |  | 0 |  |  | 1279250 |  |  | PENDING | 2026-03-05 08:05:59
92 | 15 | 16a | 1st Bill | 31.53 | 3500000 |  | 0 |  |  | 3500000 |  |  | PENDING | 2026-03-05 08:05:59
93 | 15 | 16b | 2nd running Bill | 31.53 | 3500000 |  | 0 |  |  | 3500000 |  |  | PENDING | 2026-03-05 08:05:59
94 | 15 | 16c | Final Bill | 36.94 | 4100000 |  | 0 |  |  | 4100000 |  |  | PENDING | 2026-03-05 08:05:59
95 | 16 | 17a | 1st Bill | 31.25 | 2500000 |  | 0 |  |  | 2500000 |  |  | PENDING | 2026-03-05 08:05:59
96 | 16 | 17b | 2nd running Bill | 31.25 | 2500000 |  | 0 |  |  | 2500000 |  |  | PENDING | 2026-03-05 08:05:59
97 | 16 | 17c | Final Bill | 37.5 | 3000000 |  | 0 |  |  | 3000000 |  |  | PENDING | 2026-03-05 08:05:59